## Abstract Div IV
Approval under AWP&B 2018-19 (Civil Works) under Samagra Shiksha as on 19/02/2022 Construction Division - IV
(Rs. in lacs)
S.No | Approved Head | No. of works sanctioned | Completed | In progress | Land not available/ Land issue | Not taken up | Tendering in progress | Approved cost | Funds released by SPD office | Expenditure
1 | New Primary Schools | 1 | 1 | 0 | 0 | 0 | 0 | 26.69 | 22.3 | 22.3
2 | Upgradation of PS to MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Upgradation of MS to HS | 1 | 0 | 0 | 1 | 0 | 0 | 99.39 | 45.32 | 0
4 | Upgradation of HS to HSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Boys toilet (Elementary) | 11 | 5 | 0 | 1 | 4 | 1 | 19.14 | 19.14 | 7.745
6 | Girls toilet (Elementary) | 8 | 4 | 2 | 0 | 2 | 0 | 9.76 | 4.25 | 42.496
7 | ACR (Elementary) | 49 | 25 | 0 | 24 | 0 | 0 | 349.86 | 259.43 | 128.753
8 | Boundary Walls (Elementary) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Strengthening of HS & HSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 70 | 35 | 2 | 26 | 6 | 1 | 504.84 | 350.44 | 201.294

## PS
List of New primary schools approved, 2018-19
Rs. in lacs
S.No | Division | District | Name of Habitation | Unit Cost | Approved cost | Allotted cost | Funds released | Expdenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | Tangarah | 26.69 | 26.69 | 21.48 | 22.3 | 22.3 | 100% | Completed
Total |  |  |  | 26.69 | 26.69 | 21.48 | 22.3 | 22.3

## PS to MS
List of Schools approved for upgradation from Primary to upper primary, 2018-19
Rs. in lacs
S. No. | Division | District | Name of the Habitation where UPS is Proposed | School Name | DISE Code | Unit Cost | Approved cost | Allotted Cost | Funds released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0

## MS to HS
List of Schools approved for upgradation from Upper primary to secondary (2018-19)
Rs. in lacs
S.No. | Division | District | Name of the UPS | UDISE Code | Section | Unit Cost | Approved cost | Allotted cost | Funds released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | MS Bhagani | 1130300401 | 1 section | 99.39 | 99.39 |  | 45.32 | 0 |  | Land Not available
Total | [5 empty] | 99.39 | 99.39 | 0 | 45.32 | 0

## HS to HSS
List of Schools approved for upgradation from secondary to Hr. secondary (2018-19)
Rs. in lacs
S.No. | Division | District | Name of School | UDISE code | Stream with section | Unit Cost | Approved cost | Allotted cost | Funds released by SPD office | Expdenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Total | [5 empty] | 0 | 0 | 0 | 0 | 0

## Str Sec.,Hr.sec.
List of Schools approved under strengthening secondary/Hr. secondary (2018-19)
Rs. in lacs
S.no. | Div. | District | Name of the School | UDISE Code | Year of sanction | ACR | Science Lab | Computer lab | Art/ Craft/ Culture Room | Library | Toilet | Total amount including Furniture | Allotted cost | Funds released by SPD office | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BT Ele
List of elementary Schools where Boys Toilet Approved (2018-19)
Rs. in lacs
S.No. | Division | District | School Code | School Name | Recommended | Unit Cost | Approved cost | Allotted cost | Funds released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | 1130105802 | GHSS AKHNOOR | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Not taken-up | Not required
2 | IV | JAMMU | 1130207401 | GMS ARNIA | 1 | 1.74 | 1.74 | 1.6 | 1.74 | 1.55 | 100% | Completed
3 | IV | JAMMU | 1130708801 | MS GORAKH NAGAR GIRLS | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Land not available
4 | IV | JAMMU | 1130907601 | GHS JOURIAN | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Tendereing U/p
5 | IV | JAMMU | 1131005702 | GHS PALLANWALA | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Not taken-up | Not required
6 | IV | JAMMU | 1131114501 | GHS GHO MANHASAN WNO. 7 | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Not taken-up | Not required
7 | IV | JAMMU | 1131207801 | GGHSS MIRAN SAHIB | 1 | 1.74 | 1.74 | 1.6 | 1.74 | 1.6 | 100% | Completed
8 | IV | JAMMU | 1131502305 | HS CHAK ROHI (RMSA) | 1 | 1.74 | 1.74 |  | 1.74 |  |  | Not taken-up | Not required
9 | IV | JAMMU | 1131511401 | GHS R.S. PURA WNO.1 | 1 | 1.74 | 1.74 | 1.6 | 1.74 | 1.6 | 100% | Completed
10 | IV | JAMMU | 1131900501 | GHSS NOWABAD | 1 | 1.74 | 1.74 | 1.6 | 1.74 | 1.455 | 100% | Completed
11 | IV | JAMMU | 1131902212 | GGHSS MUBARAK MANDI | 1 | 1.74 | 1.74 | 1.6 | 1.74 | 1.54 | 100% | Completed
Total |  |  |  |  | 11 | 19.14 | 19.14 | 8 | 19.14 | 7.745

## GT Ele
List of elementary Schools where Girls Toilet Approved (2018-19)
Rs. in lacs
S.No. | Division | District | School Code | School Name | Units | Unit Cost | Approved cost | Allotted cost | Funds released by SPD office | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | 1130106102 | HSS AKHNOOR W.NO.7 | 1 | 1.22 | 1.22 |  | 1.22 |  |  | Not taken up | Not requried
2 | IV | JAMMU | 1130207301 | GHS ARNIA | 1 | 1.22 | 1.22 | 1.1 | 1.22 | 1.1 | 100% | Completed
3 | IV | JAMMU | 1130605402 | H.S. NAGROTA | 1 | 1.22 | 1.22 | 1.15 | 1.22 | 1.09 | 100% | Completed
4 | IV | JAMMU | 1130905602 | MS PARGWAL | 1 | 1.22 | 1.22 |  | 1.22 |  | 50% | In progress
5 | IV | JAMMU | 1131510601 | MS MILL AREA WNO.9 | 1 | 1.22 | 1.22 | 1.15 | 1.22 | 1.12 | 100% | Completed
6 | IV | JAMMU | 1131511404 | GHSS R.S.PURA WNO1 | 1 | 1.22 | 1.22 | 1.15 | 1.22 | 0.94 | 100% | Completed
7 | IV | JAMMU | 1131710403 | HS JAMMU CANTT | 1 | 1.22 | 1.22 |  | 1.22 |  |  | Not taken up | Not required (Contonement Area)
8 | IV | JAMMU | 1131902514 | HSS SRML | 1 | 1.22 | 1.22 |  | 1.22 |  | 35% | In progress | Dispute (Brick work completed)
Total |  |  |  |  | 8 | 9.76 | 9.76 | 4.55 | 9.76 | 4.25

## ACR Ele
List of elementary Schools where ACR Approved (2018-19)
(Rs in lacs)
S.No. | Ur | District | School Name | School Code | No. of ACRs sanctioned | Unit Cost | Approved cost | Allotted cost | Funds released | Expenditure | % of Physical Status | Physical Status | Remarks
189 | IV | JAMMU | MS DHAR DHAROCHAN | 1130300901 | 1 | 7.14 | 7.14 | 5.3 | 7.03 | 5.76 | 100% | Completed
190 | IV | JAMMU | MS GURHA PATTAN | 1130302201 | 1 | 7.14 | 7.14 | 5.31 | 7.05 | 5.09 | 100% | Completed
191 | IV | JAMMU | MS CHANDIAN | 1130303702 | 1 | 7.14 | 7.14 | 5.3 | 7.03 | 5.16 | 100% | Completed
192 | IV | JAMMU | MS ORAK | 1130304201 | 1 | 7.14 | 7.14 | 5.53 | 5.53 | 4.044 | 100% | Completed
193 | IV | JAMMU | MS PARLA RABTA | 1130304703 | 1 | 7.14 | 7.14 | 6.88 | 6.88 | 6.56 | 100% | Completed
194 | IV | JAMMU | GMS KOTE | 1130306202 | 1 | 7.14 | 7.14 | 5.14 | 3.57 |  |  | Land not available
195 | IV | JAMMU | MS BISHNAH WNO.7 | 1130406601 | 1 | 7.14 | 7.14 | 4.97 | 6.37 | 4.33 | 100% | Completed
196 | IV | JAMMU | MS BASAWA | 1130501103 | 1 | 7.14 | 7.14 | 5.67 | 7.77 | 5.57 | 100% | Completed
197 | IV | JAMMU | MS SANDAL | 1130506101 | 1 | 7.14 | 7.14 | 5.67 | 3.57 |  |  | Land issue
198 | IV | JAMMU | MS CHHOURTA | 1130601101 | 1 | 7.14 | 7.14 | 5.19 | 7.14 | 5.45 | 100% | Completed
199 | IV | JAMMU | MS CHIBBA | 1130601201 | 1 | 7.14 | 7.14 |  | 5.14 |  |  | Land not available
200 | IV | JAMMU | GMS SAHNOO | 1130606401 | 1 | 7.14 | 7.14 | 4.95 | 6.33 | 4.95 | 100% | Completed
201 | IV | JAMMU | HS CHAK LARGAN | 1130701601 | 1 | 7.14 | 7.14 | 4.62 | 5.62 | 4.71 | 100% | Completed
202 | IV | JAMMU | MS KARYANI TALAB | 1130702601 | 1 | 7.14 | 7.14 | 5.4 | 7.23 | 5.67 | 100% | Completed
203 | IV | JAMMU | MS DOON | 1130702703 | 1 | 7.14 | 7.14 | 4.74 | 5.91 | 4.76 | 100% | Completed
204 | IV | JAMMU | MS RANGOORA | 1130705201 | 1 | 7.14 | 7.14 | 4 | 4.43 | 4.019 | 100% | Completed
205 | IV | JAMMU | MS SIDHRA | 1130705901 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
206 | IV | JAMMU | PS THANGER | 1130707801 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
207 | IV | JAMMU | MS RAILWAY COLONY | 1130708201 | 2 | 7.14 | 14.28 |  | 7.14 |  |  | Land not available
208 | IV | JAMMU | MS MARA KHARI | 1130708601 | 2 | 7.14 | 14.28 |  | 7.14 |  |  | Land not available
209 | IV | JAMMU | MS GORAKH NAGAR GIRLS | 1130708801 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
210 | IV | JAMMU | GMS CHANNI HIMMAT | 1130710007 | 8 | 7.14 | 57.12 |  | 28.56 |  |  | Land not available
211 | IV | JAMMU | MS CHANNI TANNA | 1130902101 | 1 | 7.14 | 7.14 | 5.34 | 7.11 | 5.34 | 100% | Completed
212 | IV | JAMMU | GMS PARGWAL | 1130905603 | 1 | 7.14 | 7.14 | 5.25 | 6.93 | 5.61 | 100% | Completed
213 | IV | JAMMU | MS N.S. PURA | 1130905611 | 1 | 7.14 | 7.14 | 6.02 | 8.47 | 5.97 | 100% | Completed
214 | IV | JAMMU | MS SAJWAL | 1130906601 | 1 | 7.14 | 7.14 | 5.04 | 6.51 | 5.03 | 100% | Completed
215 | IV | JAMMU | MS SAILAN WALI | 1131000302 | 1 | 7.14 | 7.14 | 4.68 | 5.79 | 4.61 | 100% | Completed
216 | IV | JAMMU | GMS PANJTOOT | 1131002202 | 1 | 7.14 | 7.14 | 5.29 | 7.01 | 5.57 | 100% | Completed
217 | IV | JAMMU | GMS GIGRIAL | 1131002702 | 1 | 7.14 | 7.14 | 5.03 | 10.67 | 5.03 | 100% | Completed
218 | IV | JAMMU | MS THANDI CHOI | 1131006601 | 1 | 7.14 | 7.14 | 4.38 | 5.19 | 4.34 | 100% | Completed
219 | IV | JAMMU | GMS CHAK ASLAM | 1131202101 | 1 | 7.14 | 7.14 | 5.1 | 6.63 | 5.1 | 100% | Completed
220 | IV | JAMMU | MS KHEPAR | 1131203901 | 1 | 7.14 | 7.14 | 5.72 | 7.87 | 5.61 | 100% | Completed
221 | IV | JAMMU | GMS KOTLI BHAGWAN SINGH | 1131204701 | 1 | 7.14 | 7.14 | 5.23 | 6.89 | 5.49 | 100% | Completed
222 | IV | JAMMU | GMS PHINDER | 1131206302 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
223 | IV | JAMMU | MS TOOTRAIN | 1131207701 | 1 | 7.14 | 7.14 | 4.44 | 3.57 |  |  | Land not available
224 | IV | JAMMU | MS KOTHA BHOUR | 1131700701 | 1 | 7.14 | 7.14 | 5.22 | 8.79 | 4.98 | 100% | Completed
225 | IV | JAMMU | MS SAMPURAN PUR KULLIAN | 1131708901 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
226 | IV | JAMMU | MS SHIKLIGRAN KULLIAN | 1131710601 | 1 | 7.14 | 7.14 |  | 3.57 |  |  | Land not available
227 | IV | JAMMU | GMS GUJJAR NAGAR | 1131904201 | 2 | 7.14 | 14.28 |  | 7.14 |  |  | Land not available
Total |  |  |  |  | 49 | 278.46 | 349.86 | 145.41 | 259.43 | 128.753

## BW Ele
List of elementary Schools where Boundary wall Approved at international border (2018-19)
Rs. in lacs
S.No. | Division | District | School Name | UDISE Code | Length Required | Rate Per Running Mtr | Approved Cost | Allotted Cost | Funds released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | DIV IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0