## Abstract
Division - IV Approval under AWP&B 2019-20 (Civil Works) under Samagra Shiksha as on 31/12/2021 (Rs. in lacs)
S.No | Approved Head | No. of works sanctioned | No. of schools in which works sanctioned | Completed | In progress | Land not available | Not taken up | Tendering in progress | Approved cost | Funds released | Expenditure
1 | New Primary Schools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Upgradation of PS to MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Upgradation of MS to HS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Upgradation of HS to HSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ACR (Ele.) | 5 | 1 | 0 | 0 | 0 | 0 | 5 | 35.7 | 0 | 0
6 | ACR (Sec.) | 18 | 11 | 2 | 5 | 0 | 1 | 10 | 229.14 | 50.03 | 30
7 | Strengthening (Sec.) | 277 | 120 | 27 | 122 | 29 | 0 | 99 | 3731.18 | 781.6668 | 472.915
8 | Toilet for CWSN | 68 | 68 | 0 | 0 | 0 | 0 | 68 | 132 | 0 | 0
9 | Boundary Walls | 15 | 15 | 0 | 0 | 0 | 0 | 15 | 79.8 | 0 | 0
10 | Teacher Quarter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | DIETs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Pre-Primary | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0 | 0
Total |  | 397 | 229 | 29 | 127 | 29 | 1 | 197 | 4213.42 | 831.6968 | 502.915

## PS
List of Primary Schools sanctioned for 2019-20
Rs. in lacs
S.NO | Division | District | Habitation Name | UDISE Code | Approved Cost | Allotted Cost | Funds Released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land not available
Total |  |  |  |  | 0 | 0 | 0 | 0

## HS
List of HS sanctioned for 2019-20
Rs. in lacs
S. No. | Division | District | Name of the School | UDISE Code | Section | Approved Cost | Allotted Cost | funds Released | Expenditure till date | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0

## HSS
List of HSS sanctioned for 2019-20
Rs. in lacs
S.No | Division | District | Name of School | UDISE Code | Stream | Approved Cost | Allotted Cost | Funds Released by SPD | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Total | [5 empty] | 0 | 0 | 0 | 0

## ACR (Ele)
List of Approved ACR (Elementary) 2019-20
Rs. in lacs
S.No | Division | District | School Name | School Code | No. | Unit Cost | Approved Cost | Allotted Cost | Funds Released by SPD | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | GMS CHANNI HIMMAT | 01130710007 | 5 | 7.14 | 35.7 | 0 | 0 | 0 |  | Tendering u/p
Total |  |  |  |  | 5 | 7.14 | 35.7 | 0 | 0 | 0

## ACR (Sec.)
List of Approved ACR (Secondary) 2019-20
Rs. in lacs
S.No | Division | District | School Name | School Code | No. | Unit Cost | Approved Cost | Allotted Cost | Total funds Released till date | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | GHSS ARNIA | 01130207503 | 2 | 12.73 | 25.46 |  | 0 | 0 |  | Tendering inprogress
2 | IV | JAMMU | GHSS SURINSAR | 01130705801 | 1 | 12.73 | 12.73 | 10 | 10 | 5 | 75% | In progress
3 | IV | JAMMU | GOVT. HSS MIGRANT CAMP BOHRI | 01131905009 | 1 | 12.73 | 12.73 |  | 0 | 0 |  | Not taken up | Rented
4 | IV | JAMMU | HS GIDDER GALLIAN | 01131703301 | 1 | 12.73 | 12.73 |  | 0 | 0 |  | Tendering inprogress
5 | IV | JAMMU | HSS KHARAH | 01131003701 | 2 | 12.73 | 25.46 |  | 0 | 0 |  | Tendering inprogress
6 | IV | JAMMU | HSS DANSAL | 01130601301 | 2 | 12.73 | 25.46 | 19.33 | 19.3233 | 16.995 |  | completed
7 | IV | JAMMU | HSS JHAJJAR KOTLI | 01130602808 | 2 | 12.73 | 25.46 |  | 0 | 0 | 25% | In progress
8 | IV | JAMMU | HSS JHIRI | 01131106606 | 1 | 12.73 | 12.73 |  | 5 | 0 |  | Tendering inprogress
9 | IV | JAMMU | HSS JINDRAH | 01130602701 | 2 | 12.73 | 25.46 | 15.71 | 15.71 | 8 | 0.9 | In progress
10 | IV | JAMMU | HSS KATHAR | 01130603801 | 2 | 12.73 | 25.46 |  | 0 | 0 |  | Tendering inprogress
11 | IV | JAMMU | HSS SALEHAR | 01130205607 | 2 | 12.73 | 25.46 |  | 0 | 0 |  | Tendering inprogress
Total |  |  |  |  | 18 |  | 229.14 | 45.04 | 50.0333 | 29.995
0

## Strengthening (Sec.)
List of Approved Schools for Strengthening 2019-20 (Till date)
Rs. in lacs
S. No. | Division | District | School Name | School Code | Year of sanction | Science Lab | Art/Craft Room | Library | Computer Room | Total | Total amount including Furniture | Allotted cost | funds Released | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | GGHSS MIRAN SAHIB | 01131207801 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
2 | IV | JAMMU | GHS AGORE | 01130300101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 20.16 | 20.1612 | 17.306 | 100% | Completed
3 | IV | JAMMU | GHS BADYAL BRAHAMANA | 01131200202 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 19.28 | 8.3543 | 0 |  | Land not available
4 | IV | JAMMU | GHS BASTI GULAB GARH | 01131500901 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 20.45 | 9.8412 | 0 |  | Tendering in progress
5 | IV | JAMMU | GHS BHAGWATI NAGAR | 01131905201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
6 | IV | JAMMU | GHS BHOUR CAMP WARD NO.1 | 01131700801 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
7 | IV | JAMMU | GHS BUJ MANDIR | 01131107101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.58 | 18.5512 | 14.898 | 100% | Completed
8 | IV | JAMMU | GHS CITY CHOWK | 01131902503 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.58 | 0 | 0 |  | Land not available
9 | IV | JAMMU | GHS DABLEHAR | 01131502704 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 8.997 | 8.997 | 8.955 | 100% | Completed
10 | IV | JAMMU | GHS DEOLI | 01130402601 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
11 | IV | JAMMU | GHS DOMANA | 01130306002 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.83 | 9.83 | 0 | 35% | In Progress
12 | IV | JAMMU | GHS GHO MANHASAN WNO. 7 | 01131114501 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
13 | IV | JAMMU | GHS GOLE GUJRAL | 01131105102 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.17 | 8.8412 | 8.84 | 75% | In Progress
14 | IV | JAMMU | GHS GOLE PANJPEER | 01131904402 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
15 | IV | JAMMU | GHS JANIPUR COLONY | 01131903601 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Land not available
16 | IV | JAMMU | GHS JOURIAN | 01130907601 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 10.32 | 10.3144 | 10.32 | 100% | Completed
17 | IV | JAMMU | GHS KHOUR | 01131003916 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
18 | IV | JAMMU | GHS MARH BAGH (RMSA) | 01131108801 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.45 | 19.4512 | 9.84 | 35% | In Progress
19 | IV | JAMMU | GHS PALLANWALA | 01131005702 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
20 | IV | JAMMU | GHS RAJPURA MANGOTRIAN | 01131901601 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Land not available
21 | IV | JAMMU | GHS RANPUR MULLIANIAN | 1131508601 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
22 | IV | JAMMU | GHS RESHAM GHAR | 01131901201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
23 | IV | JAMMU | GHS SAID GARH | 01130205401 | 2019-20 | 1 | 1 | 1 | 1 | 4 |  | 42.44 | 0 | 0 | 25% | In Progress
24 | IV | JAMMU | GHS SANGRAM PUR | 01131112101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 20.499 | 9.8412 | 9.84 | 70% | In Progress
25 | IV | JAMMU | GHS SARORE | 01130405401 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.96 | 9.96 | 9.96 | 100% | Completed
26 | IV | JAMMU | GHS SATARYAN | 01131509202 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
27 | IV | JAMMU | GHS SEER BLAH | 01131509401 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
28 | IV | JAMMU | GHS SHAMA CHAK | 01131112701 | 2019-20 | 0 | 0 | 0 | 1 | 1 | 12.72 |  | 0 | 0 |  | Tendering in progress
29 | IV | JAMMU | GHS SIMBAL CAMP | 01131206204 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.99 | 9.99 | 9.99 | 100% | Completed
30 | IV | JAMMU | GHS SOHANJANA | 01131709401 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.31 | 9.31 | 6.197 | 70% | In Progress
31 | IV | JAMMU | GHS TOPHSHERKHANIA | 01131900401 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Land not available
32 | IV | JAMMU | GHSS AKHNOOR | 01130105802 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.267 | 12.4 | 9.267 | 100% | Completed
33 | IV | JAMMU | GHSS ARNIA | 01130207503 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
34 | IV | JAMMU | GHSS BAHU FORT | 01130709301 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 8.48 | 8.4844 | 7.758 | 100% | Completed
35 | IV | JAMMU | GHSS CANAL ROAD | 01131900510 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 29.456 | 29.456 | 0 | 25% | In Progress
36 | IV | JAMMU | GHSS GHOU MANHASSAN | 01131114507 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
37 | IV | JAMMU | GHSS R.S.PURA WNO1 | 01131511404 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
38 | IV | JAMMU | GHSS REHAL DHAMELIAN | 01130405304 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 40 | 30 | 0 | 75% | In Progress
39 | IV | JAMMU | GHSS REHARI | 01131901406 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 10.61 | 12.4144 | 10.41 | 100% | Completed
40 | IV | JAMMU | GHSS SATWARI | 01131710402 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
41 | IV | JAMMU | GHSS SURINSAR | 01130705801 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 41.887 | 40 | 25.255 | 75% | In Progress
42 | IV | JAMMU | GIRLS HSS SHASTRI NAGAR | 01130707307 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 8.51 | 6.4244 | 0 |  | Land issue
43 | IV | JAMMU | HS BADYAL BRAHAMANA | 01131200201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.25 | 10.8412 | 0 | 25% | In Progress
44 | IV | JAMMU | HS BATHINDI | 01130700901 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Land not available
45 | IV | JAMMU | HS BHALWAL BRAHMANA | 01130101201 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.187 | 12 | 9.187 | 100% | Completed
46 | IV | JAMMU | HS BHATYARI(RMSA). | 01130600701 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 42 | 0 | 0 | 25% | In Progress
47 | IV | JAMMU | HS CHAK MAJRA | 01130201201 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 41.72 | 0 | 0 | 25% | In Progress
48 | IV | JAMMU | HS CHAK MALAL | 01131000801 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
49 | IV | JAMMU | HS CHOWADI | 01130709710 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Land not available
50 | IV | JAMMU | HS DANA CHAPPRI | 01130501401 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.35 | 9.35 | 6.307 | 75% | In Progress
51 | IV | JAMMU | HS DATYAL | 01131001601 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 43 | 0 | 0 | 25% | In Progress
52 | IV | JAMMU | HS DEVIPUR | 01130101801 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.11 | 18.1112 | 17.392 | 100% | Completed
53 | IV | JAMMU | HS GANDHI NAGAR | 01130707602 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 29.488 | 0 | 29.488 | 25% | In Progress
54 | IV | JAMMU | HS GAJANSOO | 01131104301 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.58 | 14.8412 | 4.782 | 25% | In Progress
55 | IV | JAMMU | HS GIGRIAL | 01131002701 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 43 | 0 | 0 | 25% | In Progress
56 | IV | JAMMU | HS GOL GUJRAL | 01131105101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
57 | IV | JAMMU | HS GONDLA | 01130600301 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.86 | 19.86 | 9.84 | 75% | In Progress
58 | IV | JAMMU | HS GORDA | 01130301901 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
59 | IV | JAMMU | HS H.P. SIDHAR | 01131002901 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
60 | IV | JAMMU | HS JAMMU CANTT | 01131710403 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
61 | IV | JAMMU | HS KALU CHAK | 01130709511 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
62 | IV | JAMMU | HS KANGRAIL | 01130302801 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 56.69 | 15 | 0 | 25% | In Progress
63 | IV | JAMMU | HS KATAL BATAL | 01130603901 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 44.5 | 0 | 0 | 25% | In Progress
64 | IV | JAMMU | HS KATHAR | 01130503301 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
65 | IV | JAMMU | HS KHAIRI | 01130403704 | 2019-20 | 1 | 1 | 0 | 1 | 3 | 38.26 |  | 0 | 0 |  | Tendering in progress
66 | IV | JAMMU | HS KHANA CHARGAL | 01130702701 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 44.25 | 0 | 0 | 25% | In Progress
67 | IV | JAMMU | HS KIRPIND | 01131204301 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
68 | IV | JAMMU | HS KOTLI TANDA | 01130102101 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
69 | IV | JAMMU | HS KOTMAIRA | 01131004301 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
70 | IV | JAMMU | HS MAJUA UTTAMI | 01130404301 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
71 | IV | JAMMU | HS MATHWAR | 01130303801 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 43.39 | 0 | 0 | 25% | In Progress
72 | IV | JAMMU | HS MERA MANDRIAN | 01130103801 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.05 | 9.05 | 6 | 25% | In Progress
73 | IV | JAMMU | HS NARYANA | 01131003904 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 30.5 | 0 | 0 | 25% | In Progress
74 | IV | JAMMU | HS NATHAL | 01130504801 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.29 | 9.8412 | 0 | 25% | In Progress
75 | IV | JAMMU | HS PANGARI | 01130505201 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 40 | 0 | 0 | 25% | In Progress
76 | IV | JAMMU | HS PANJGARAIN | 01130904301 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
77 | IV | JAMMU | HS PINDI SAROCHAN | 01130205101 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 41.72 | 0 | 0 | 25% | In Progress
78 | IV | JAMMU | HS PULL TAWI | 01130706501 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Land not available
79 | IV | JAMMU | HS RAH SALYOTE | 01130502601 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
80 | IV | JAMMU | HS RAIPUR | 01130306301 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.25 | 9.25 | 6.305 | 35% | In Progress
81 | IV | JAMMU | HS RAIPUR SATWARI | 01131708101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
82 | IV | JAMMU | HS RANJAN | 01130302403 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
83 | IV | JAMMU | HS SIMBAL CAMP | 01131207601 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 41.29 | 0 | 0 | 25% | In Progress
84 | IV | JAMMU | HS SUNAIL | 01130105201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.34 | 25 | 18.214 | 100% | Completed
85 | IV | JAMMU | HS SUNGAL | 01130506201 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 41.89 | 41.89 | 20.31 | 75% | In Progress
86 | IV | JAMMU | HS TARRAH | 01130607801 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Land not available
87 | IV | JAMMU | HS TREVA | 01130206101 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 20.26 | 20.26 | 19.685 | 100% | Completed
88 | IV | JAMMU | HSS JULLAKA MOHALLA | 01131903513 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 10.46 | 10.46 | 10.46 | 25% | In Progress
89 | IV | JAMMU | HSS KHARAH | 01131003701 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
90 | IV | JAMMU | HSS ALLAH | 01130200201 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 29.88 | 0 | 0 | 25% | In Progress
91 | IV | JAMMU | HSS BHALWAL | 01130300601 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 20.2 | 15.8412 | 15.84 | 100% | Completed
92 | IV | JAMMU | HSS BHOUR CAMP, WARD-2 | 01131700703 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 10.1 | 10.0944 | 9.917 | 100% | Completed
93 | IV | JAMMU | HSS HSS BISHNAH (BOYS) | 01130407101 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.96 | 4.9244 | 0 | 25% | In Progress
94 | IV | JAMMU | HSS CENTRAL BASIC | 01131902513 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Land not available
95 | IV | JAMMU | HSS CHOWKI-CHOURA | 01130501109 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 19.11 | 9.8412 | 9.84 | 75% | In Progress
96 | IV | JAMMU | HSS DABLEHAR | 01131502701 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 0 | 0 |  |  | Tendering in progress
97 | IV | JAMMU | HSS DHAKAR | 01131001801 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.4 | 6.4244 | 0 | 25% | In Progress
98 | IV | JAMMU | HSS DOMANA | 01130306012 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.83 | 0 | 0 | 35% | In Progress
99 | IV | JAMMU | HSS DORI DAGER | 01130501301 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 |  | 0 | 0 |  | Tendering in progress
100 | IV | JAMMU | HSS GHAROTA | 01130301801 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 43.97 | 14 | 0 | 25% | In Progress
101 | IV | JAMMU | HSS HARI SINGH | 01131903410 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 0 | 0 |  | Tendering in progress
102 | IV | JAMMU | HSS JHAJJAR KOTLI | 01130602808 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 | 25% | In Progress
103 | IV | JAMMU | HSS JHIRI | 01131106606 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 |  | 15.589 | 0 |  | Tendering in progress
104 | IV | JAMMU | HSS JINDRAH | 01130602701 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 36.01 | 36.01 | 23.55 | 75% | In Progress
105 | IV | JAMMU | HSS JOURIAN | 01130907702 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 29 | 0 | 0 | 25% | In Progress
106 | IV | JAMMU | HSS KATHAR | 01130603801 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 |  | 0 | 0 |  | Tendering in progress
107 | IV | JAMMU | HSS MARH | 01131108704 | 2019-20 | 1 | 0 | 1 | 0 | 2 | 31.21 |  | 0 | 0 |  | Tendering in progress
108 | IV | JAMMU | HSS MIGRANTCAMP JAGTI | 01130602310 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.29 | 9.29 | 8.3 | 100% | Completed
109 | IV | JAMMU | HSS MUTHI | 01131900201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 25.48 | 24.5025 | 8.33 | 25% | In Progress
110 | IV | JAMMU | HSS NARARI BALA | 01130104304 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 8.85 | 8.85 | 8.424 | 100% | Completed
111 | IV | JAMMU | HSS NOWABAD | 01131904403 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 25.48 | 17.8412 | 5.241 | 25% | In Progress
112 | IV | JAMMU | HSS PALLANWALA | 01131005711 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
113 | IV | JAMMU | HSS PALOURA | 01131900301 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.54 | 10.6704 | 9.537 | 100% | Completed
114 | IV | JAMMU | HSS PARGWAL (ND) | 01130905610 | 2019-20 | 1 | 1 | 1 | 0 | 3 | 43.97 | 40 | 30 | 30 | 25% | In Progress
115 | IV | JAMMU | HSS SAI | 01131507201 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.53 | 6 | 0 | 25% | In Progress
116 | IV | JAMMU | HSS SALEHAR | 01130205607 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 |  | 0 | 0 |  | Tendering in progress
117 | IV | JAMMU | HSS SOHAL | 01130103201 | 2019-20 | 0 | 1 | 0 | 1 | 2 | 25.48 | 18.58 | 18.5812 | 17.92 | 100% | Completed
118 | IV | JAMMU | HSS SUNJWAN | 01130709904 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 40 | 15 | 0 | 75% | In Progress
119 | IV | JAMMU | HSS. KAH POHTA | 01130606201 | 2019-20 | 0 | 1 | 0 | 0 | 1 | 12.76 | 9.83 | 9.83 | 9.21 | 100% | Completed
120 | IV | JAMMU | LHS BAIN BAJALTA | 01130700301 | 2019-20 | 1 | 1 | 1 | 1 | 4 | 56.69 | 42.694 | 0 | 0 | 25% | In Progress
Total | [5 empty] | 46 | 118 | 45 | 68 | 277 | 3731.18 | 1626.385 | 781.6668 | 472.915

## CWSN Toilets
List of Approved CWSN Toilet 2019-20
Rs. in lacs
S.No | Division | District | School Name | School Code | Approved Cost | Allotted Cost | Funds Released by SPD | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | HS BARUI (RMSA) | 01130101101 | 2 | 0 | 0 | 0 |  | Tendering in progress
2 | IV | JAMMU | HS BHALWAL BRAHMANA | 01130101201 | 2 | 0 | 0 | 0 |  | Tendering in progress
3 | IV | JAMMU | HS KOTLI TANDA | 01130102101 | 2 | 0 | 0 | 0 |  | Tendering in progress
4 | IV | JAMMU | HS KOTGARHI (RMSA) | 01130103601 | 2 | 0 | 0 | 0 |  | Tendering in progress
5 | IV | JAMMU | HS MERA MANDRIAN | 01130103801 | 2 | 0 | 0 | 0 |  | Tendering in progress
6 | IV | JAMMU | HS SUNAIL | 01130105201 | 2 | 0 | 0 | 0 |  | Tendering in progress
7 | IV | JAMMU | GHS SAID GARH | 01130205401 | 2 | 0 | 0 | 0 |  | Tendering in progress
8 | IV | JAMMU | HS KANGRAIL | 01130302801 | 2 | 0 | 0 | 0 |  | Tendering in progress
9 | IV | JAMMU | HS SAROTE (RMSA) | 01130305201 | 2 | 0 | 0 | 0 |  | Tendering in progress
10 | IV | JAMMU | HS BHATYARI | 01130400201 | 2 | 0 | 0 | 0 |  | Tendering in progress
11 | IV | JAMMU | HS CHAK JARLANA (RMSA) | 01130400901 | 2 | 0 | 0 | 0 |  | Tendering in progress
12 | IV | JAMMU | HS CHAK MURAR (RMSA) | 01130401201 | 2 | 0 | 0 | 0 |  | Tendering in progress
13 | IV | JAMMU | GHS DEOLI | 01130402601 | 2 | 0 | 0 | 0 |  | Tendering in progress
14 | IV | JAMMU | HS KHAIRI | 01130403704 | 2 | 0 | 0 | 0 |  | Tendering in progress
15 | IV | JAMMU | GHS SARORE | 01130405401 | 2 | 0 | 0 | 0 |  | Tendering in progress
16 | IV | JAMMU | GHS NUGRAN (RMSA) | 01130407301 | 2 | 0 | 0 | 0 |  | Tendering in progress
17 | IV | JAMMU | HS DANA CHAPPRI | 01130501401 | 2 | 0 | 0 | 0 |  | Tendering in progress
18 | IV | JAMMU | HS RAH SALYOTE | 01130502601 | 2 | 0 | 0 | 0 |  | Tendering in progress
19 | IV | JAMMU | HS KATHAR | 01130503301 | 2 | 0 | 0 | 0 |  | Tendering in progress
20 | IV | JAMMU | HS PANGARI | 01130505201 | 2 | 0 | 0 | 0 |  | Tendering in progress
21 | IV | JAMMU | HS JHANG | 01130505401 | 2 | 0 | 0 | 0 |  | Tendering in progress
22 | IV | JAMMU | HS SUNGAL | 01130506201 | 2 | 0 | 0 | 0 |  | Tendering in progress
23 | IV | JAMMU | HS KATAL BATAL | 01130603901 | 2 | 0 | 0 | 0 |  | Tendering in progress
24 | IV | JAMMU | LHS BAIN BAJALTA | 01130700301 | 2 | 0 | 0 | 0 |  | Tendering in progress
25 | IV | JAMMU | HS BATHINDI | 01130700901 | 2 | 0 | 0 | 0 |  | Tendering in progress
26 | IV | JAMMU | HS DEELI (RMSA) | 01130702201 | 2 | 0 | 0 | 0 |  | Tendering in progress
27 | IV | JAMMU | HS KHANA CHARGAL | 01130702701 | 2 | 0 | 0 | 0 |  | Tendering in progress
28 | IV | JAMMU | HS DIGIANA(RMSA). | 01130706701 | 2 | 0 | 0 | 0 |  | Tendering in progress
29 | IV | JAMMU | HS GANDHI NAGAR | 01130707602 | 2 | 0 | 0 | 0 |  | Tendering in progress
30 | IV | JAMMU | HS QASIM NAGAR (RMSA) | 01130708301 | 2 | 0 | 0 | 0 |  | Tendering in progress
31 | IV | JAMMU | HS KALU CHAK | 01130709511 | 2 | 0 | 0 | 0 |  | Tendering in progress
32 | IV | JAMMU | HS SANDHI | 01130709603 | 2 | 0 | 0 | 0 |  | Tendering in progress
33 | IV | JAMMU | HS CHATTA (RMSA) | 01130709906 | 2 | 0 | 0 | 0 |  | Tendering in progress
34 | IV | JAMMU | HS KALEETH | 01130903901 | 2 | 0 | 0 | 0 |  | Tendering in progress
35 | IV | JAMMU | HS PANJGARAIN | 01130904301 | 2 | 0 | 0 | 0 |  | Tendering in progress
36 | IV | JAMMU | GHS JOURIAN | 01130907601 | 2 | 0 | 0 | 0 |  | Tendering in progress
37 | IV | JAMMU | HS DATYAL | 01131001601 | 2 | 0 | 0 | 0 |  | Tendering in progress
38 | IV | JAMMU | HS GIGRIAL | 01131002701 | 2 | 0 | 0 | 0 |  | Tendering in progress
39 | IV | JAMMU | HS KALAH (RMSA) | 01131003301 | 2 | 0 | 0 | 0 |  | Tendering in progress
40 | IV | JAMMU | GHS KHOUR | 01131003916 | 2 | 0 | 0 | 0 |  | Tendering in progress
41 | IV | JAMMU | GHS PALLANWALA | 01131005702 | 2 | 0 | 0 | 0 |  | Tendering in progress
42 | IV | JAMMU | HS CHAK RALI (RMSA) | 01131102301 | 2 | 0 | 0 | 0 |  | Tendering in progress
43 | IV | JAMMU | HS GANJANSOO | 01131104301 | 2 | 0 | 0 | 0 |  | Tendering in progress
44 | IV | JAMMU | GHS KAHANA CHAK | 01131106202 | 2 | 0 | 0 | 0 |  | Tendering in progress
45 | IV | JAMMU | HS SANDWAN | 01131111401 | 2 | 0 | 0 | 0 |  | Tendering in progress
46 | IV | JAMMU | GHS SANGRAM PUR | 01131112101 | 2 | 0 | 0 | 0 |  | Tendering in progress
47 | IV | JAMMU | GHS SHAMA CHAK | 01131112701 | 2 | 0 | 0 | 0 |  | Tendering in progress
48 | IV | JAMMU | GHS GHO MANHASAN WNO. 7 | 01131114501 | 2 | 0 | 0 | 0 |  | Tendering in progress
49 | IV | JAMMU | GHS RANGPUR MOULANIAN | 01131500801 | 2 | 0 | 0 | 0 |  | Tendering in progress
50 | IV | JAMMU | GHS BASTI GULAB GARH | 01131500901 | 2 | 0 | 0 | 0 |  | Tendering in progress
51 | IV | JAMMU | HS CHAK ROHI (RMSA) | 01131502305 | 2 | 0 | 0 | 0 |  | Tendering in progress
52 | IV | JAMMU | GHS DABLEHAR | 01131502704 | 2 | 0 | 0 | 0 |  | Tendering in progress
53 | IV | JAMMU | GHS KALYOEN (RMSA) | 01131504701 | 2 | 0 | 0 | 0 |  | Tendering in progress
54 | IV | JAMMU | GHS RANPUR MULLIANIAN | 01131508601 | 2 | 0 | 0 | 0 |  | Tendering in progress
55 | IV | JAMMU | GHS SATARYAN | 01131509202 | 2 | 0 | 0 | 0 |  | Tendering in progress
56 | IV | JAMMU | HS BARJALA (RMSA) | 01131700601 | 2 | 0 | 0 | 0 |  | Tendering in progress
57 | IV | JAMMU | GHS BHOUR CAMP WARD NO.1 | 01131700801 | 2 | 0 | 0 | 0 |  | Tendering in progress
58 | IV | JAMMU | GHS CHATHA PIND (RMSA) | 01131702301 | 2 | 0 | 0 | 0 |  | Tendering in progress
59 | IV | JAMMU | HS LACHHMAN PURA | 01131705801 | 2 | 0 | 0 | 0 |  | Tendering in progress
60 | IV | JAMMU | HS RAIPUR SATWARI | 01131708101 | 2 | 0 | 0 | 0 |  | Tendering in progress
61 | IV | JAMMU | GHS SOHANJANA | 01131709401 | 2 | 0 | 0 | 0 |  | Tendering in progress
62 | IV | JAMMU | GHS TOPHSHERKHANIA | 01131900401 | 2 | 0 | 0 | 0 |  | Tendering in progress
63 | IV | JAMMU | GHS RESHAM GHAR | 01131901201 | 2 | 0 | 0 | 0 |  | Tendering in progress
64 | IV | JAMMU | GHS RAJPURA MANGOTRIAN | 01131901601 | 2 | 0 | 0 | 0 |  | Tendering in progress
65 | IV | JAMMU | GHS CITY CHOWK | 01131902503 | 2 | 0 | 0 | 0 |  | Tendering in progress
66 | IV | JAMMU | GHS JANIPUR COLONY | 01131903601 | 2 | 0 | 0 | 0 |  | Tendering in progress
67 | IV | JAMMU | GHS GOLE PANJPEER | 01131904402 | 2 | 0 | 0 | 0 |  | Tendering in progress
68 | IV | JAMMU | GHS BHAGWATI NAGAR | 01131905201 | 2 | 0 | 0 | 0 |  | Tendering in progress
Total |  |  |  |  | 136 | 0 | 0 | 0

## Boundary wall
List of Approved Schools for Boundary Wall 2019-20
Rs. in lacs
S.No | Division | District | School Name | UDISE Code | Length required | rate per running mtr | Approved Cost | Allotted Cost | Total funds Released till date | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | JAMMU | GMS KATHAR | 01130603802 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
2 | IV | JAMMU | MS BADGAL KALAN | 01130100301 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
3 | IV | JAMMU | MS BELI AZMAT | 01131100701 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
4 | IV | JAMMU | MS CHHAJWAL | 01131001401 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
5 | IV | JAMMU | MS DOHAL | 01131002301 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
6 | IV | JAMMU | MS JADH | 01130903701 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
7 | IV | JAMMU | MS JADH BRAHMANA | 01130903703 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
8 | IV | JAMMU | MS KALYAR | 01130303802 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
9 | IV | JAMMU | MS KAMDHINI NALLAH | 01131005202 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
10 | IV | JAMMU | MS KOOL KALAN | 01130202801 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
11 | IV | JAMMU | MS PINDI | 01130905701 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
12 | IV | JAMMU | MS RATHUA | 01131110901 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
13 | IV | JAMMU | MS SHOWA | 01130305401 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
14 | IV | JAMMU | PS L. KOR JAGIR | 01130604401 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
15 | IV | JAMMU | PS NAGOLA | 01130605301 | 80 | 0.0665 | 5.32 |  | 0 | 0 |  | Tendering in progress
Total |  |  |  |  | 1200 | 0.9975 | 79.8 | 0 | 0 | 0

## Tr. Quarters
List of Approved Schools for TEACHER QUARTER 2019-20
Rs. in lacs
S.No | Division | District | Name of Proposed School to be supported with the Quarters | UDISE code of to be supported schools | Approved Cost | Allotted Cost | Funds Released by SPD | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Total |  |  |  |  | 0 | 0 | 0 | 0

## DIET
List of Approved DIETs 2019-20
Rs. in lacs
S. No | Division | District & Name of DIETs | Activity | Approved Cost | Allotted Cost | Funds Released by SPD | Expenditure | % of Physical Status | Physical Status | Remarks
1 | IV | Jammu | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 0 | 0 | 0 | 0

## Pre-primary support
List of Schools Approved for Pre-Primary Support (2019-20)
Rs. in lacs
S. No | Name of the District | Name of Zone | Name of School | UDISE Code | Approved Cost | Allotted Cost | Funds Released by DSEK/SPD | Expenditure | Physical Status | Remarks
1 | Jammu | Akhnoor | MS GODHAN | 1130102601 | 0.4
2 | Jammu | Arnia | GMS ALLAH | 1130200202 | 0.4
3 | Jammu | Bhalwal | MS LOWER THATHER | 1130305604 | 0.4
4 | Jammu | Bishnah | MS KARYAL BRAHMANA | 1130403401 | 0.4
5 | Jammu | ChowkiChoura | MS BARDAL KHURD | 1130500701 | 0.4
6 | Jammu | Dansal | MS BAMYAL | 1130600302 | 0.4
7 | Jammu | Gandhi Nagar | MS KARYANI TALAB | 1130702601 | 0.4
8 | Jammu | Jammu | HSS PALOURA | 1131900301 | 0.4
9 | Jammu | Jourian | MS JADH | 1130903701 | 0.4
10 | Jammu | Khour | MS NarBehra | 1131001803 | 0.4
11 | Jammu | Marh | MS SOHAGNI | 1131113301 | 0.4
12 | Jammu | Miran Sahib | HS JINDER MELU (RMSA) | 1131203301 | 0.4
13 | Jammu | RS Pura | MS MOTTEY | 1131507401 | 0.4
14 | Jammu | SATWARi | MODEL MIDDLE SCHOOL SATWARI | 1131710401 | 0.4
Total |  |  |  |  | 5.6 | 0 | 0 | 0 | 0 | 0